## Sheet1
not used |  |  |  |  | not used | not used |  |  | not used | not used | not used | not used | not used
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
| 20563 | 13/EE/0397 | 132094 | C&C | NIMRAD | 2017-02-24 | 2017-02-28 | No |  | 0 |  |  | N/A | 2016-03-10 | 2016-03-10 | 2016-10-21 | 2016-06-15 | 2017-03-08 | 2017-02-28 |  | 2017-03-09 | [10 empty] | Window still open as at end of Q4 - End of April
| 30186 | 14/WM/1170 | 161147 | C&C | COMPARE | 2017-01-11 | 2017-03-24 | No |  | 73 |  |  | No | 2016-08-24 | 2016-08-24 | 2017-01-11 | 2016-05-23 | 2017-03-31 | 2017-03-24 |  | 2017-03-31 |  |  |  | Y |  |  |  | Y |  | Y | Delay in from 6th of Jan to 24th Feb in receiving contracts back from Sponsor. The further delays by locla pharmacy arrangements. | Sponsor & NHS Provider
| 89527 | 14/NE/1180 | 145170 | C&C | UK GRIS | 2017-01-16 | 2017-03-20 | Yes | 2017-03-27 | 63 | 7 | 70 | Yes | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-03-14 | 2014-03-14 |  | 2017-03-20
90972 | 16/SC/0655 | 212212 | C&C | Knee Replacement Bandaging Study (KReBS) | 2017-04-03 | 2017-04-05 | Yes | 2017-06-02 | 3 | 56 | 59 | Yes | 2016-12-07 | 2016-12-07 | 2017-04-03 | 2017-02-08 | 2017-04-05 | 2017-04-05 |  | 2017-04-05
27971 | 15/EM/0055 | 167115 | C&C | RIGHT-2 | 2016-10-04 | 2017-04-05 | Yes | 2017-04-13 | 178 |  | 174 | No | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-06-15 | 2017-01-30 | 2017-01-30 |  | 2017-04-05 |  |  |  |  | Y |  |  | Y |  | Y | Training of the ward staff and paramedics | NHS Provider and Sponsor
11722 | 12/LO/0515 | 95626 | C&C | OPTIMA- SGH | 2017-02-27 | 2017-04-05 | No |  | 37 |  |  |  | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2016-08-03 | 2017-04-05 | 2017-04-05 |  | 2017-04-05 | [5 empty] | Y | Y |  |  |  | Lack of eligible patients | NHS Provider
31397 | 14/SC/1416 | 156215 | C&C | IGNITE | 2017-03-30 | 2017-05-11 | No |  | 1900-02-02 |  |  | No | 2017-07-22 | 2017-07-22 | 2017-03-30 | 2016-10-04 | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | [5 empty] | Y |  |  | Y |  | No eligible patients seen coming through hospital | NHS provider
87771 | 16/SC/0454 | 206701 | C&C | NASH | 2017-05-08 | 2017-05-23 |  |  | 1900-01-14 |  |  |  | 2016-04-05 | 2016-06-29 | 2017-05-08 | 2016-11-09 | 2017-05-11 | 2017-05-23 |  | 2017-05-23
39106 | 15/WM/0268 | 180518 | C&C | ENRICH | 2017-05-23 | 2017-07-12 |  |  | 39 |  |  |  | 2017-03-29 | 2017-03-29 | 2017-05-23 | 2017-05-23 | 2017-07-04 | 2017-07-12 |  | 2017-07-12 | [10 empty] | Chemocare presciption delays due to pharmacy staffing
84321 | 16/WH/0396 | 210511 | C&C | ASCEND ND | 2017-02-21 | 2017-04-13 | Yes | 2017-05-11 | 51 |  | 79 | no | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-03 | 2017-03-28 | 2017-03-28 |  | 2017-04-13 |  |  |  |  | Y |  |  |  |  | Y | Protocol issue. Long run in period (8 weeks) between consenting and randomisation, fewer suitable patients, reduced staffing. | Sponsor
87307 | 16/NS/0094 | 206213 | C&C | BISTRO | 2017-04-07 | 2017-05-12 | Yes | 2017-07-18 | 35 |  | 102 | No | 2017-01-12 | 2017-01-12 | 2017-04-07 | 2017-10-04 | 2017-05-04 | 2017-05-04 |  | 2017-05-12 |  |  |  |  | Y | [5 empty] | Urine sampling required, reduced staffing
94346 | 17/SC/0142 | 215503 | C&C | The 65 Trial | 2017-06-27 | 2017-07-04 | No |  | 7 |  |  |  | 2017-05-05 | 2017-05-05 | 2017-06-27 | 2017-04-24 | 2017-07-04 | 2017-07-04 |  | 2017-07-04