## Sheet1
not used |  |  |  |  | not used | not used |  |  | not used | not used | not used | not used | not used
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
30186 | 14/WM/1170 | 161147 | C&C | COMPARE | 2017-01-11 | 2017-03-24 | No |  | 73 |  |  | No | 2016-08-24 | 2016-08-24 | 2017-01-11 | 2016-05-23 | 2017-03-31 | 2017-03-24 |  | 2017-03-31 |  |  |  | Y |  |  |  | Y |  | Y | Delay in from 6th of Jan to 24th Feb in receiving contracts back from Sponsor. The further delays by locla pharmacy arrangements. | Sponsor & NHS Provider
89527 | 14/NE/1180 | 145170 | C&C | UK GRIS | 2017-01-16 | 2017-03-20 | Yes | 2017-03-27 | 63 | 7 | 70 | Yes | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-03-14 | 2017-03-14 |  | 2017-03-20
90972 | 16/SC/0655 | 212212 | C&C | Knee Replacement Bandaging Study (KReBS) | 2017-04-03 | 2017-04-05 | Yes | 2017-06-02 | 3 | 56 | 59 | Yes | 2016-12-07 | 2016-12-07 | 2017-04-03 | 2017-02-08 | 2017-04-05 | 2017-04-05 |  | 2017-04-05
11722 | 12/LO/0515 | 95626 | C&C | OPTIMA- SGH | 2017-02-27 | 2017-04-05 | No |  | 37 |  |  |  | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2016-08-03 | 2017-04-05 | 2017-04-05 |  | 2017-04-05 | [5 empty] | Y | Y |  |  |  | Lack of eligible patients | NHS Provider
31397 | 14/SC/1416 | 156215 | C&C | IGNITE | 2017-03-30 | 2017-05-11 | No |  | 34 |  |  | No | 2017-07-22 | 2017-07-22 | 2017-03-30 | 2016-10-04 | 2017-05-11 | 2017-05-11 |  | 2017-05-11 | [5 empty] | Y |  |  | Y |  | No eligible patients seen coming through hospital | NHS provider
87771 | 16/SC/0454 | 206701 | C&C | NASH | 2017-05-08 | 2017-05-23 | No |  | 15 |  |  | No | 2016-04-05 | 2016-06-29 | 2017-05-08 | 2016-11-09 | 2017-05-11 | 2017-05-23 |  | 2017-05-23 | [6 empty] | Y | Y |  | Y | External delays with arranging Service Level Agreement for MRI support. Patient failed screening. | NHS Provider
94346 | 17/SC/0142 | 215503 | C&C | The 65 Trial | 2017-06-27 | 2017-07-04 | Yes | 2017-07-27 | 7 | 23 | 30 | Yes | 2017-05-05 | 2017-05-05 | 2017-06-27 | 2017-04-24 | 2017-07-04 | 2017-07-04 |  | 2017-07-04
87307 | 16/NS/0094 | 206213 | C&C | BISTRO | 2017-04-07 | 2017-05-12 | Yes | 2017-07-18 | 35 | 67 | 102 | No | 2017-01-12 | 2017-01-12 | 2017-04-07 | 2017-10-04 | 2017-05-04 | 2017-05-04 |  | 2017-05-12 |  |  |  |  | Y | [5 empty] | Urine sampling required, reduced staffing
84321 | 16/WH/0396 | 210511 | C&C | ASCEND ND | 2017-02-21 | 2017-04-13 | Yes | 2017-05-11 | 51 | 28 | 79 | no | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-03 | 2017-03-28 | 2017-03-28 |  | 2017-04-13 |  |  |  |  | Y |  |  |  |  | Y | Protocol issue. Long run in period (8 weeks) between consenting and randomisation, fewer suitable patients, reduced staffing. | Sponsor
39106 | 15/WM/0268 | 180518 | C&C | ENRICH | 2017-05-23 | 2017-07-12 | No |  | 39 |  |  | No | 2017-03-29 | 2017-03-29 | 2017-05-23 | 2017-05-23 | 2017-07-04 | 2017-07-12 |  | 2017-07-12 |  |  |  |  | y | y |  |  |  |  | Chemocare presciption delays due to pharmacy staffing
86315 | 16/SC/0542 | 208245 | C&C | OMASPECT | 2017-06-26 | 2017-07-20 | Yes | 2017-07-21 | 24 | 1 | 26 | Yes | 2016-09-26 | 2016-09-26 | 2017-06-26 | 2016-11-09 | 2017-07-06 | 2017-07-20 |  | 2017-07-20
| 16/EE/0463 | 214371 | C&C | COMPLEEMENT-1 | 2017-08-09 | 2017-09-07 | Yes | 2017-10-06 | 30 | 29 | 59 | Yes | 2017-03-01 | 2017-03-01 | 2017-08-09 | 2017-01-30 | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | [9 empty] | y | Delayed opening due to Chemocare update for study (shortage of Pharmacist staff) | NHS Provider
31701 | 16/NE/0238 | 204031 | C&C | SENIOR RITA | 2017-07-10 | 2017-08-31 | Yes | 2017-09-15 | 52 | 15 | 67 | Yes | 2016-08-08 | 2016-12-19 | 2017-07-10 | 2017-06-21 | 2017-07-31 | 2017-07-31 |  | 2017-08-31
32120 | 17/NE/0027 | 215796 | C&C | CReST2 | 2017-07-10 | 2017-10-03 | No | 2017-12-13 | 85 | 71 | 156 | No | 2017-01-20 | 2017-04-03 | 2017-04-20 | 2017-04-03 | 2017-08-23 | 2017-10-03 |  | 2017-08-23 |  |  |  | Y | [5 empty] | Y | Sponsor delays in providing the green light. Site delays in ordering necessary equipment and the timley delivery of this. | Sponsor and NHS Provider
32118 | 16/NW/0718 | 204299 | C&C | RDSI-LC | 2017-07-27 | 2017-08-24 | Yes | 2017-09-11 | 28 | 18 | 46 | Yes | 2016-12-05 | 2016-12-09 | 2017-03-29 | 2016-12-19 | 2017-08-24 | 2017-08-24 |  | 2017-08-24
92639 | 17/LO/0618 | 223878 | C&C | IMVIGOR | 2017-08-16 | 2017-09-28 | No |  | 52 |  |  | No | 2017-03-15 | 2017-03-15 | 2017-08-02 | 2017-07-19 | 2017-09-28 | 2017-09-28 |  | 2017-09-28 | [5 empty] | Y |  |  |  | y | Delayed opening due to Chemocare update for study (shortage of Pharmacist staff). No eligible patients found despite 5 screeended | NHS Provider
100032 | 17/EM/0339 | 223211 | C&C | AKRENDO | 2017-11-23 | 13/12/2017 | No |  | 20 |  |  |  | 2017-12-06 | 2017-07-05 | 23/11/2017 | 2017-09-26 | 2017-12-05 | 13/12/2017 |  | 13/12/2017
91303 | 17/LO/0792 | 223470 | C&C | PARALLAX | 2017-09-28 | 2017-10-12 | Yes | 2017-11-01 | 14 | 20 | 34 | Yes | 2017-09-28 | 2017-02-27 | 2017-09-28 | 2017-06-30 | 2017-09-28 | 2017-10-12 |  | 2017-10-12

## Sheet2
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22