## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
| 16/EE/0463 | 214371 | C&C | COMPLEEMENT-1 | 2017-08-09 | 2017-09-07 | Yes | 2017-10-06 | 30 | 29 | 59 | 2017-03-01 | 2017-03-01 | 2017-08-09 | 2017-01-30 | 2017-09-07 | 2017-09-07 |  | 2017-09-07 | [9 empty] | y | Delayed opening due to Chemocare update for study (shortage of Pharmacist staff) | NHS Provider
31701 | 16/NE/0238 | 204031 | C&C | SENIOR RITA | 2017-07-10 | 2017-08-31 | Yes | 2017-09-15 | 52 | 15 | 67 | 2016-08-08 | 2016-12-19 | 2017-07-10 | 2017-06-21 | 2017-07-31 | 2017-07-31 |  | 2017-08-31
92639 | 17/LO/0618 | 223878 | C&C | IMVIGOR | 2017-08-16 | 2017-09-28 | Yes | 2018-05-21 | 52 |  | 279 | 2017-03-15 | 2017-03-15 | 2017-08-02 | 2017-07-19 | 2017-09-28 | 2017-09-28 |  | 2017-09-28 | [5 empty] | Y |  |  |  | y | Delayed opening due to Chemocare update for study (shortage of Pharmacist staff). No eligible patients found despite 5 screeended | NHS Provider
100032 | 17/EM/0339 | 223211 | C&C | AKRENDO | 2017-11-23 | 13/12/2017 | No |  | 20 |  |  | 2017-12-06 | 2017-07-05 | 23/11/2017 | 2017-09-26 | 2017-12-05 | 13/12/2017 |  | 13/12/2017 | [6 empty] | Y |  |  |  | No eligible patients happy to consent. | NHS provider
91303 | 17/LO/0792 | 223470 | C&C | PARALLAX | 2017-09-28 | 2017-10-12 | Yes | 2017-11-01 | 14 | 20 | 34 | 2017-09-28 | 2017-02-27 | 2017-09-28 | 2017-06-30 | 2017-09-28 | 2017-10-12 |  | 2017-10-12
100283 | 17/LO/1134 | 228166 | C&C | PREP Impact | 23/11/2017 | 2018-02-13 | Yes | 2018-02-19 | 83 |  | 82 | 2017-08-14 | 2017-08-14 | 2017-11-23 | 2017-08-03 | 2018-02-08 | 2018-02-13 |  | 2018-02-13 | Y |  |  |  | Y | [5 empty] | Delayed CaC review due to staff capacity issues | NHS Provider
90578 | 17/LO/1367 | 225049 | C&C | IPSOS | 2018-02-12 | 2018-02-21 | No |  | 9 |  |  | 2017-03-13 | 2017-03-13 | 24/01/2018 | 2017-09-19 | 2018-01-24 | 2018-02-21 |  | 2018-02-21 | y |  |  | y | [6 empty] | Delays in receiving final login details for study portals. | Sponsor
103796 | 17/NE/0377 | 233847 | C&C | DIALIZE | 2018-02-26 | 2018-03-09 | No |  | 0 |  |  | 2018-12-06 | 2017-12-06 | 2018-02-26 | 2018-02-19 | 2018-02-19 | 2018-02-26 |  | 2018-03-09 | [6 empty] | Y |  |  | Y | Patients approached but do not want to take part. Recruiting time restricted to daytime and not twilight hours. | NHS Provider
84384 | 16/EM/0186 | 173279 | C&C | STAR TREC | 2018-04-17 |  | No |  |  |  |  | 04/04/2017 | 04/04/2017 | 2018-04-17 | 2016-10-31 | 17/05/2018 | 17/05/2018 |  | 17/05/2018 |  |  |  | Y | [6 empty] | Delays with return of contract from Sponsor
104874 | 18/LO/0141 | 233922 | C&C | OPINION | 2018-06-04 |  | No |  |  |  |  | 2018-03-23 | 2018-04-16 | 2018-06-04 | 2018-03-23 | 2018-05-29 | 2018-06-04 |  | 2018-06-13 | [6 empty] | Y |  | Y |  | Screened 4 patients, but no one yet eligible - strict criteria

## Sheet2
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16

## Sheet3
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18
2017-05-19
2017-05-20
2017-05-21
2017-05-22
2017-05-23
2017-05-24
2017-05-25
2017-05-26
2017-05-27
2017-05-28
2017-05-29
2017-05-30
2017-05-31
2017-06-01
2017-06-02
2017-06-03
2017-06-04
2017-06-05
2017-06-06
2017-06-07
2017-06-08
2017-06-09
2017-06-10
2017-06-11
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16
2017-06-17
2017-06-18
2017-06-19
2017-06-20
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28
2017-06-29
2017-06-30
2017-07-01
2017-07-02
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05
2017-08-06
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10